## DRMM Score
| Score | 0 - 2 | 3 - 4 | 5 - 6 | 7 - 8 | 9 - 10
| Finding | Non-Existent | In Devel | Defined | Maturing | Resilient
| Final Score | 6.5196
Category |  | DR Strategy defined I | DR Playbook Complete II | Relevant Listing of DR Personnel III | RTO Achievable IV | Staff preparedness V | Issues/Risk
|  | WEIGHT | WEIGHT | WEIGHT | WEIGHT | WEIGHT
|  | 30 | 15 | 5 | 5 | 45
Class 1
Network Infra
| Internet | 9 | 7 | 5 | 5 | 8
| DR Server Network | 9 | 7 | 5 | 5 | 8
| VPN | 9 | 7 | 5 | 5 | 8
| Gigamon | 0 | 0 | 0 | 0 | 0 | I. DR strategy needs to be defined
DNS
| DNS Servers (F5 GTM) | 9 | 6 | 5 | 8 | 6
| Infoblox Servers | 9 | 7 | 5 | 8 | 8
AD
| Forest Root Controllers | 9 | 7 | 5 | 5 | 8
| DC (corp.contoso.com) | 9 | 7 | 5 | 5 | 8
| DC (sts.contoso.com) | 9 | 7 | 5 | 5 | 8
Auth Infra
| RSA Server | 9 | 7 | 5 | 5 | 8
| Radius | 9 | 7 | 5 | 8 | 8
| CyberArk | 9 | 7 | 5 | 8 | 8
File Servers
| DFS | 9 | 7 | 5 | 9 | 8
| sFTP Servers | 9 | 0 | 0 | 0 | 0
| Sharepoint | 9 | 0 | 0 | 0 | 0
Mail Servers
| Ironport | 9 | 8 | 5 | 9 | 6
| Exchange Servers | 9 | 5 | 5 | 6 | 8
Web
| Load Balancer (F5 LTM) | 9 | 4 | 4 | 4 | 4
Web Servers
SAN
| Recover Point | 9 | 7 | 5 | 8 | 8
Voice Infra
| CCM | 9 | 7 | 7 | 8 | 8
Class 2 | Peoplesoft Fin | 6 | 8 | 4 | 5 | 8
CMS
| Peoplesoft HR | 5 | 4 | 4 | 5 | 4
Portal Applications
| SSO | 9 | 0 | 0 | 0 | 0
AVERAGE |  | 8.3043 | 5.4783 | 4.087 | 5.2609 | 6.087
Note on E11: Gupta, Manish: Stale listing of DR personnel
Note on G11: Gupta, Manish: - DR Drill? - Manual workaround needs to be documented
Note on E12: Gupta, Manish: Stale listing of DR personnel
Note on G12: Gupta, Manish: - DR Drill - Manual workaround needs to be documented
Note on E13: Gupta, Manish: Stale listing of DR personnel
Note on G13: Gupta, Manish: - DR Drill - Manual workaround needs to be documented
Note on E14: Gupta, Manish: Stale listing of DR personnel
Note on E16: Gupta, Manish: Stale listing of DR personnel
Note on G16: Gupta, Manish: - DR Drill - Manual workaround needs to be documented
Note on E17: Gupta, Manish: Stale listing of DR personnel
Note on E19: Gupta, Manish: Stale listing of DR personnel
Note on E20: Gupta, Manish: Stale listing of DR personnel
Note on D27: Gupta, Manish: - Documentation stale and needs to be updated
Note on E27: Gupta, Manish: Stale listing of DR personnel
Note on D28: Gupta, Manish: - Documentation stale and needs to be updated
Note on D29: Gupta, Manish: - Documentation stale and needs to be updated
Note on D31: Gupta, Manish: - Documentation stale and needs to be updated
Note on E31: Gupta, Manish: Stale listing of DR personnel
Note on D32: Gupta, Manish: - Documentation stale and needs to be updated
Note on E32: Gupta, Manish: Stale listing of DR personnel
Note on G32: Gupta, Manish: - Manual workaround needs to be documented
Note on G34: Gupta, Manish: All config needs to be in DR
Note on D37: Gupta, Manish: - Documentation stale and needs to be updated
Note on E37: Gupta, Manish: Stale listing of DR personnel
Note on D39: Gupta, Manish: - Documentation stale and needs to be updated
Note on E39: Gupta, Manish: Stale listing of DR personnel
Note on C41: Gupta, Manish: No DNS strategy
Note on D41: Gupta, Manish: - Documentation stale and needs to be updated
Note on E41: Gupta, Manish: Stale listing of DR personnel
Note on G41: Gupta, Manish: - Manual Workaround needs to be documented
Note on C43: Gupta, Manish: No DNS strategy
Note on D43: Gupta, Manish: - Documentation stale and needs to be updated
Note on E43: Gupta, Manish: Stale listing of DR personnel

## DRMM Trend
Date | DRMM Score | Non-Existent | In Development | Defined | Maturing | Highly Resilient | Comment | Score | 0 - 2 | 3 - 4 | 5 - 6 | 7 - 8 | 9 - 10
2018-11-20 | 4.85 | 2 | 2 | 2 | 2 | 2 |  | Finding | Non-Existent | In Devel | Defined | Maturing | Resilient
2018-12-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-01-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-02-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-03-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-04-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-05-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-06-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-07-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-08-01 | 4.85 | 2 | 2 | 2 | 2 | 2
2019-09-17 | 6.52 | 2 | 2 | 2 | 2 | 2
2019-10-01 | 6.52 | 2 | 2 | 2 | 2 | 2
2019-11-01 | 6.52 | 2 | 2 | 2 | 2 | 2
|  | 2 | 2 | 2 | 2 | 2

## Other Issues (hidden)
Other issues/Risk Factors
Communication Plan needs to be updated
Do we have multiple communication channels (to avoid SPOF) of communication channel
Call trees, list, staff names needs to be updated
Document manual workaround
We need to review RTO and RPO for each service
Designation of a Business Continuity Manager (ML)?
DR Drill atleast once a year (can be segmented by service/application). Where drill not possible conduct walkthru
Formalize periodic audit of DR procedure

## Task Tracker
Meeting Date -> |  |  | 2019-01-16 |  | 2019-04-09 |  | 2019-05-22 |  | 2019-07-02 |  | 2019-08-13 |  | 2019-09-17 |  | 2019-10-15 |  | 2019-11-15
Items | Description | Group | Due Date | Status | New DD | Status | New DD | Status | New DD | Status | New DD | Status | New DD | Status | New DD | Status | New DD | Status
GTM /DNS | Setup DNS in GTM the way it used to be in 2009 | DBOPS | 2019-01-31 |  | 2019-04-30 | CM to clarify apollo.nas.edu | 2019-06-05 |  | Next Meeting |  | 2019-09-20 |  | 2019-09-25 | work next week |  | Transferred to NetOPS
GTM/ MX record | Setup DNS in GTM the way it used to be in 2009 | DBOPS | 2019-01-31 |  | 2019-04-30 |  | 2019-06-05 |  | Next Meeting |  | 2019-09-20 |  | 2019-09-25 | work next week |  | Transferred to NetOPS
sFTP Server | Setup sFTP server Workday interface | DBOPS | 2019-02-15 | Done | 2019-05-15 |  | 2019-06-05 |  |  | Done (No Documentation)
RECOVERPOINT |  | NCC | 2019-01-31 | Done
MASTER DOCUMENT | Update DR Master Document | CT | 2019-01-31 |  |  |  |  | Done
List of reponsibilities | Update List of Responsibilities for DR | CT | 2019-01-31 |  |  |  |  | Done
DR network review | Review DR network plans | EA | 2 wk from 3/7 | Done
DR Test AD and DNS (plan) | Create DR test plan for AD DC and Infoblox DNS | NSE | [6 empty] | Next Meeting |  | 2019-09-30 | Meet on 9/30 to review plan, test to be conducted on 10/18 |  | Test plan was presented for AD, DNS test. Reschedule to discuss few open points on 11th Oct |  | mercury test results to next month. Dec 1st to be test date. Report to be run against all DMZ servers to make sure rushmore is included.
Dr Test plan external DNS | Create DR test plan DNS Servers | UNIX | [6 empty] | Next Meeting |  |  | JH out |  | To be done by 10/8 |  | Test date set to dec 1st